## Sheet1
ITEM | JOB DESCRIPTION | MODULE | DURATION | CAEZAR | LORENZ | C#DEV
1 | > Minor adjustments or revisions until production ready. > Target: Teaser and TigaSouth | Motion Graphics | 8
2 | Page routes for navigation other than homepage, like blog page, terms, privacy, etc. | WordPress Site | 12
| Minor adjustments and bug fixing to quality control of the implementation. | WordPress Site | 8
3 | Application for API access and setting up client configuration | Google SDK | 8
| Write a code that will bind Google token to our native signin and signup. | Google SDK | 24
| Minor adjustments and bug fixing to quality control of the implementation. | Google SDK | 6
4 | Application for API access and setting up client configuration. | Facebook SDK | 8
| Write a code that will bind Facebook token to our native signin and signup. | Facebook SDK | 24
| Minor adjustments and bug fixing to quality control of the implementation. | Facebook SDK | 6
5 | Write the backend RestAPI for signin and implement on client, using username and password and return token to the user. | Native SDK | 12 |  | 12
| Write the backend RestAPI for signup with email notification using our own official email to send activation key to the given user email then handle password reset on client. | Native SDK | 16 |  | 16
| Write the backend RestAPI for forgot password that will send new password reset activation key to the user email and handle password reset on client. | Native SDK | 16 |  | 16
| Minor adjustments and bug fixing to quality control of the implementation. | Native SDK | 4
6 | Design and Develop a Database for handling this user networking. | FEED LISTVIEWS | 8 |  | 8 | 8
| On success user signin or complete signup, the application will automatically ask for primary user information like name, photo, banner, etc. | FEED LISTVIEWS | 16 | 8 | 8
| On Home page, Write a backend restapi that will initially request for 12 post entry and then dynamically increment 5 post entry if user is near at the end of post. Next to the, implement the displaying of this data on the client side. | FEED LISTVIEWS | 32 | 16 | 16
| On Profile page (either local or other), Write a backend restapi that will initially request for 12 post entry and then dynamically increment 5 post entry if user is near at the end of post. Next to the, implement the displaying of this data on the client side. | FEED LISTVIEWS | 24 | 12 | 12
| On Profile and Home, make a simple system that will distinguish what type of post will be display on the feed. Every type should be easily distinguishable. | FEED LISTVIEWS | 12 |  |  | 12
| Quality control and checking for bugs or any unhandled exception. | FEED LISTVIEWS | 8
7 | Design and Develop a Database for handling this user networking. | USER ACTIVITY | 8 |  | 8 | 8
| Make the RestApi for INSERT, UPDATE, DELETE off activity log. | USER ACTIVITY | 16 |  | 16
| Make a Backend UI for Displaying and managing logs. | USER ACTIVITY | 24 |  | 24
| Implement the displaying of user log into Notification. | USER ACTIVITY | 24 |  |  | 24
| Quality control and checking for bugs or any unhandled exception. | USER ACTIVITY | 8
8 | Design and Develop a Database for handling this user networking. | ADVISORIES | 8 |  | 8 | 8
| Make the RestApi for INSERT, UPDATE, DELETE off post. | ADVISORIES | 16 |  | 16
| Make a Backend UI for Displaying and managing post. | ADVISORIES | 24 |  | 24
| Implement the displaying of user log into Notification. | ADVISORIES | 24 |  |  | 24
| Quality control and checking for bugs or any unhandled exception. | ADVISORIES | 8
| Design and Develop a Database for handling this user networking. | SETTINGS | 8 |  | 8
| Edit Profile Subpage Front + Back | SETTINGS | 24 |  | 12
| My Address Subpage Front + Back | SETTINGS | 16 |  | 8
| Change Password Subpage Front + Back | SETTINGS | 16 |  | 8
| Link Account Subpage Front + Back | SETTINGS | 16 |  | 8
| Settings Notification Subpage Front + Back | SETTINGS | 8 |  | 4
| Help Center Subpage Front + Back | SETTINGS | 16 |  | 8
| Terms Subpage Front + Back | SETTINGS | 16 |  | 8
| Privacy Subpage Front + Back | SETTINGS | 16 |  | 8
| FAQs Subpage Front + Back | SETTINGS | 16 |  | 8
| Quality control and checking for bugs or any unhandled exception. | SETTINGS | 8
9 | Design and Develop a Database for handling this user networking. | FEED INPUTS | 8 |  | 8
| Either on Home or Profile, write a backend RestApi for inserting new post type of status, then implement it on the client side, user should display a modal popup editor for showing Status post. | FEED INPUTS | 24 | 12 | 12
| Either on Home or Profile, write a backend RestApi for inserting new post type of selling, then implement it on the client side, user should display a modal popup editor for showing Selling of post. | FEED INPUTS | 24 | 12 | 12
| Either on Home or Profile, write a backend RestApi for inserting new post type of request, then implement it on the client side, user should display a modal popup editor for showing Request of post | FEED INPUTS | 24 | 12 | 12
| Quality control and checking for bugs or any unhandled exception. | FEED INPUTS | 6
10 | Design and Develop a Database for handling this user networking | RATINGS / REVIEWS | 8 |  | 8
| Make a RestAPI for USER PROFILE DATA by USER ID to be consume on PROFILE display. | RATINGS / REVIEWS | 16 |  | 16
| Make a RestAPI for INSERT, UPDATE, and DELETE of ratings / reviews. | RATINGS / REVIEWS | 16 |  | 16
| Make a RestAPI for post, transact, and ratings. | RATINGS / REVIEWS | 8 |  | 8
| Make a simple backend ui for checking review system log | RATINGS / REVIEWS | 24 |  | 24
| Implement on the client side the display of the reviews to profile and other profile page. - Add leave a review button on profile page if not yours and have a previous transaction. | RATINGS / REVIEWS | 24 |  | 12
| Quality control and checking for bugs or any unhandled exception. | RATINGS / REVIEWS | 4
11 | Design and Develop a Database for handling this wallet system. | WALLET SYSTEM | 8 |  | 8 | 8
| Make a simple backend ui for checking wallet system log. | WALLET SYSTEM | 24 |  | 24
| Make a RestAPI for inserting, transfer currency to other user. | WALLET SYSTEM | 24 |  | 24
| Implement on the client side the display of the logs and transaction as well as the summary of logs and visualization. | WALLET SYSTEM | 24 |  |  | 24
| Quality control and checking for bugs or any unhandled exception. | WALLET SYSTEM | 8
12 | Design and Develop a Database for handling this referral system. - Note: Successful Referal -> if Manual Verification is Success | REFERRAL SYSTEM | 8 |  | 8
| Make a simple backend ui for referral logs . | REFERRAL SYSTEM | 16 |  | 16
| Write a WordPress routing override for short link of referral and perform the crediting mechanism for this referral or whatever to implement. Either Credits or Voucher/Coupons | REFERRAL SYSTEM | 24 |  | 24
| Implement on the client side for showing a button or ui for sharing referral. | REFERRAL SYSTEM | 16 |  | 16
| Quality control and checking for bugs or any unhandled exception. | REFERRAL SYSTEM | 8
13 | Research and Meeting for the best Design and Structure. | USOCKETNET DEPLOY | 6 |  |  | 6
| Embed the UsocketNet PLC to Xamarin project with Chat module only. | USOCKETNET DEPLOY | 24 |  |  | 24
| Implement on the client side on sending and receiving messages. | USOCKETNET DEPLOY | 20 |  |  | 20
| Quality control and checking for bugs or any unhandled exception. | USOCKETNET DEPLOY | 6
14 | Research and Meeting for the best Design and Structure. | CLIENT MESSAGING | 8 |  | 8
| Design and Develop an efficient action flow for sending and receiving realtime data from user to user. Database: usn_message | CLIENT MESSAGING | 8 |  | 8
| Make a RestAPI that will post the message to wordpress from a success message callaback | CLIENT MESSAGING | 16 |  | 16
| Implement on the client that will send a message to a specific wp user by ID and return a callback. | CLIENT MESSAGING | 24 |  |  | 24
| Quality control and checking for bugs or any unhandled exception. | CLIENT MESSAGING | 8
15 | Design and Develop a backend for handling this navigation system. | COURIER NAVIGATION | 8 |  | 8
| From transaction page of mover, after the user click a transaction to enable view, the navigation page will show current direction view Server. | COURIER NAVIGATION | 16 |  | 16
| From transaction page of mover, after the user click a transaction to enable view, the navigation page will show current direction view client. | COURIER NAVIGATION | 24 |  |  | 24
| Implement multiple dropoff direction api and ask google for estimated time of arrival based on current and previous speed through RestAPI. | COURIER NAVIGATION | 16 |  | 16
| Implement multiple dropoff direction api and ask google for estimated time of arrival based on current and previous speed through Client. | COURIER NAVIGATION | 24 |  |  | 24
| User be able to show info about the request just by pressing (i) logo on the top upper side of the page through RestAPI | COURIER NAVIGATION | 8 |  | 8
| User be able to show info about the request just by pressing (i) logo on the top upper side of the page through Client. | COURIER NAVIGATION | 8 |  |  | 8
| User can Cancel and Complete the current active transactions with tabview on the different active transaction through RestApi | COURIER NAVIGATION | 12 |  | 12
| User can Cancel and Complete the current active transactions with tabview on the different active transaction through client | COURIER NAVIGATION | 12 |  |  | 12
| Quality control and checking for bugs or any unhandled exception. | COURIER NAVIGATION | 8
16 | Research and Meeting for the best Design and Structure. | COURIER TRANSACTION | 8 |  | 8 | 8
| Make a RestAPI for INSERT, UPDATE, DELETE any transaction logs. | COURIER TRANSACTION | 16 |  | 16
| Make a Backend UI for managing this logs. | COURIER TRANSACTION | 24 |  | 24
| Implement displaying of user transaction to the client. | COURIER TRANSACTION | 24 |  |  | 24
| Quality control and checking for bugs or any unhandled exception. | COURIER TRANSACTION | 8
17 | Research and Meeting for the best Design and Structure. | COURIER DASHBOARD | 8 |  | 8
| Make a RestAPI for all the group of data that must be shown by user id. | COURIER DASHBOARD | 16 |  | 16
| Make a Backend UI for showing transacations or we can also filter display. | COURIER DASHBOARD | 24 |  | 24
| Design a dashboard for showing data that needs to be shown. | COURIER DASHBOARD | 8 |  |  | 8
| Layout a dashboard for showing all significant data utilizing different charts. | COURIER DASHBOARD | 24 | 12 |  | 12
| Quality control and checking for bugs or any unhandled exception. | COURIER DASHBOARD | 8
18 | Research and Meeting for the best Design and Structure. | COURIER MESSAGING | 8 |  | 8 | 8
| From the transaction page, messaging will use the id of that user to have an active conversation on the chat page. | COURIER MESSAGING | 16 | 8 | 8
| Make a RestAPI for getting and receiving recent messages to next page. | COURIER MESSAGING | 16 |  | 16
| Implement on the client side on sending and receiving messages on client side. | COURIER MESSAGING | 24 |  |  | 24
| Quality control and checking for bugs or any unhandled exception. | COURIER MESSAGING | 8
19 | Research and Meeting for the best Design and Structure. | COURIER VERIFY | 4 |  | 8
| User will be able to apply for verification and upload list of required and optional data | COURIER VERIFY | 24 | 12 | 12
| Make a backend ui for accepting and comment the user about the status or issue. | COURIER VERIFY | 16 |  | 16
| User will be able to received comments and reply to comments about this on client side. | COURIER VERIFY | 24 |  | 24
| Quality control and checking for bugs or any unhandled exception. | COURIER VERIFY | 6
20 | Research and Meeting for the best Design and Structure. | GROCERY | 8 |  | 8 | 8
| RestAPI for database hook upon plugin or module init | GROCERY | 4 |  | 4
| RestAPI for getting items by category | GROCERY | 16 |  | 16
| Make a backend ui for adding, editing, removing grocery item. | GROCERY | 16 |  | 16
| Display the item depending on what’s requested | GROCERY | 24 |  |  | 24
| Quality control and checking for bugs or any unhandled exception. | GROCERY | 8
21 | Research and Meeting for the best Design and Structure. | MARKET | 16 |  | 16 | 16
| RestAPI for getting product by Newest filter with Loop Query | MARKET | 8 |  | 8
| RestAPI for getting product by Popular filter with Loop Query | MARKET | 8 |  | 8
| RestAPI for getting product by Featured filter with Loop Query | MARKET | 8 |  | 8
| Make a backend UI for managing market products. | MARKET | 20 |  | 20
| Display the item depending on what’s requested | MARKET | 24 |  |  | 24
| Quality control and checking for bugs or any unhandled exception. | MARKET | 8
22 | Research and Meeting for the best available Payment Gateway | eCommerce FRONT | 8 |  | 8
| StoreFront RestAPI storage of configs. | eCommerce FRONT | 12 |  | 12
| StoreFront client side. | eCommerce FRONT | 20 |  |  | 20
| Orders Listing RestAPI | eCommerce FRONT | 12 |  | 12
| Orders Listing Client side | eCommerce FRONT | 20 |  |  | 20
| Tracking RestAPI | eCommerce FRONT | 12 |  | 12
| Tracking Client | eCommerce FRONT | 20 |  |  | 20
| Cart RestAPI | eCommerce FRONT | 12 |  | 12
| Cart Client | eCommerce FRONT | 20 |  |  | 20
| Checkout RestAPI | eCommerce FRONT | 12 |  | 12
| Checkout Client | eCommerce FRONT | 20 |  |  | 20
| Payment RestAPI | eCommerce FRONT | 16 |  | 12
| Payment Client | eCommerce FRONT | 24 |  |  | 24
| Quality control and checking for bugs or any unhandled exception. | eCommerce FRONT | 8
23 | Research and Meeting for the best available Payment Gateway | eCommerce BACKEND | 8 |  | 8 | 8
| Storefront Manager Server | eCommerce BACKEND | 16 |  | 16
| Storefront Manager Client | eCommerce BACKEND | 24 |  |  | 24
| Orders list Server | eCommerce BACKEND | 16 |  | 16
| Order list Client | eCommerce BACKEND | 24 |  |  | 24
| Transaction Server | eCommerce BACKEND | 12 |  | 12
| Transaction Client | eCommerce BACKEND | 20 |  |  | 20
| Product Server | eCommerce BACKEND | 12 |  | 12
| Product Client | eCommerce BACKEND | 20 |  |  | 20
| Category Server | eCommerce BACKEND | 12 |  | 12
| Category Client | eCommerce BACKEND | 20 |  |  | 20
| Voucher Server | eCommerce BACKEND | 12 |  | 12
| Voucher Client | eCommerce BACKEND | 20 |  |  | 20
| Reviews Server | eCommerce BACKEND | 16 |  | 16
| Review Client | eCommerce BACKEND | 24 |  |  | 24
| Document and Validation Server | eCommerce BACKEND | 16 |  | 16
| Document and Validation Client | eCommerce BACKEND | 24 |  |  | 24
| Quality control and checking for bugs or any unhandled exception. | eCommerce BACKEND | 8
24 | Research and Meeting for the best available Payment Gateway | eCommerce POS | 8 |  | 8 | 8
| POS Counter Layout | eCommerce POS | 16 | 16
| POS Counter Server | eCommerce POS | 40 |  | 40
| POS Counter Client | eCommerce POS | 48 | 12 |  | 36
| Transactions Server | eCommerce POS | 16 |  | 16
| Transactions Client | eCommerce POS | 24 | 8 |  | 16
| Quality control and checking for bugs or any unhandled exception. | eCommerce POS | 8
25 | Research and Meeting for the best available Payment Gateway | PAYMENT | 8 |  | 8
| PAYPAL – From application to implementing of sdk to the app. Making RestAPI to server and the client to process current transaction. | PAYMENT | 32 | 16 | 16
| GCASH - From application to implementing of sdk to the app. Making RestAPI to server and the client to process current transaction. | PAYMENT | 32 | 16 | 16
| Quality control and checking for bugs or any unhandled exception. | PAYMENT | 8
26 | Writing to publishing content for our developer PlayStore and AppStore. | PUBLISHING | 12
| Writing content for Android and IOS like description and capturing Previews. | PUBLISHING | 8
| Publishing on PlayStore with all related Meta binding to related sites. | PUBLISHING | 6
| Publishing on AppStore with all related Meta binding to related sites. | PUBLISHING | 6
| Quality control and double checking all data published and setting linkage to our site. - Make sure SignUp and SignIn is totally working. - Make sure Google/Facebook login is working properly. - Make sure Firebase analytics is working properly. | PUBLISHING | 24
27 | Installation testing | TESTING | 4 |  | 2
| Target Device and OS testing | TESTING | 4 |  | 2
| UI and UX testing | TESTING | 4 |  | 2
| Functionality Testing | TESTING | 4 |  | 2
| Interrupt testing | TESTING | 4 |  | 2
| Data network testing | TESTING | 4 |  | 2
| Hardware keys testing | TESTING | 4 |  | 2
| Performance Testing | TESTING | 4 |  | 2
| Load testing | TESTING | 4 |  | 2
| Security testing | TESTING | 4 |  | 2
|  |  | 2512 | 510 | 1220 | 782 | HOURS
|  |  | 314 | 63.75 | 152.5 | 97.75 | DAYS